## Project Timeline Data
Tasks | Start Date | Days to Complete | Person Responsible | Feasibility | Risks | Legend
vb#1 | 2018-02-08 | 1 | Saim Zahid |  |  | vb = visual bug
vb#2 | 2018-02-25 | 2 | Yanting Zhang |  |  | pb = player bug
vb#3 | 2018-02-16 | 0.41 | Yanting Zhang | about 1 hour or less |  | eb = enemy bug
vb#4 | 2018-02-25 | 3 | Yi Chen |  |  | ab = audio bug
vb#5 | 2018-02-19 | 2 | Tian Guo
vb#6 | 2018-02-06 | 1 | Jonathan Yu
pb#1 | 2018-02-02 | 0.41 | Jonathan Yu | about 1 hour or less
pb#2 | 2018-02-02 | 0.41 | Jonathan Yu | about 1 hour or less
pb#3 | 2018-02-16 | 1 | Saim Zahid
pb#4 | 2018-02-23 | 3 | Yi Chen
pb#5 | 2018-02-13 | 2 | Yanting Zhang
pb#6 | 2018-02-20 | 0.41 | Tian Guo | about 1 hour or less
pb#7 | 2018-02-16 | 3 | Saim Zahid
pb#8 | 2018-02-20 | 0.41 | Jonathan Yu
pb#9 | 2018-02-20 | 0.41 | Tian Guo
pb#10 | 2018-02-20 | 0.41 | Yanting Zhang
eb#1 | 2018-02-02 | 0.41 | Yi Chen | about 1 hour or less
eb#2 | 2018-02-13 | 0.41 | Tian Guo | about 1 hour or less
eb#3 | 2018-02-02 | 2 | Yanting Zhang
eb#4 | 2018-02-02 | 3 | Jonathan Yu |  | If stoping all coroutines doesn't work than this might be a very hard fix
eb#5 | 2018-02-16 | 0.41 | Jonathan Yu | about 1 hour or less
eb#6 | 2018-02-23 | 3 | Yanting Zhang
eb#7 | 2018-02-02 | 0.41 | Yanting Zhang | about 1 hour or less
eb#8 | 2018-02-16 | 0.41 | Yi Chen | about 1 hour or less
eb#9 | 2018-02-23 | 0.41 | Yanting Zhang | about 1 hour or less
eb#10 | 2018-02-13 | 0.41 | Saim Zahid | about 1 hour or less
ab#1 | 2018-02-23 | 0.41 | Yanting Zhang
ab#2 | 2018-02-23 | 0.41 | Tian Guo
ab#3 | 2018-02-23 | 0.41 | Yi Chen
ub#1 | 2018-02-13 | 2 | Yanting Zhang
ub#2 | 2018-02-02 | 0.41 | Yi Chen
ub#3 | 2018-02-13 | 2 | Tian Guo
ub#4 | 2018-02-02 | 0.41 | Yi Chen
ib#1 | 2018-02-04 | 0.41 | Yanting Zhang
ib#2 | 2018-02-04 | 0.41 | Tian Guo
ib#3 | 2018-02-04 | 0.41 | Saim Zahid
ib#4 | 2018-02-04 | 0.41 | Saim Zahid
Air Combo Attack | 2018-03-02 | 2 | Jonathan Yu
Level Fades | 2018-03-09 | 1 | Yi Chen
Save Progession | 2018-03-16 | 3 | Jonathan Yu
player Respawn Intro | 2018-03-05 | 3 | Tian Guo
Damage Display | 2018-03-06 | 2 | Jonathan Yu
Combo Text Display | 2018-03-18 | 4 | Saim Zahid
EnemyTweaks | 2018-02-02 | 2 | Jonathan Yu
Level 2 | 2018-03-13 | 4 | Jonathan Yu